## README
Insperity Project Portfolio — Holonic Semantic Governance Program
Prepared by Jeffrey Wallk, The Value Enablement Group, LLC · illustrative planning portfolio, not an Insperity-endorsed document
How this list was derived
Roadmap: Insperity Intelligence Holarchy (IIH) four-phase plan — Phase 0 Foundation (M1–2), Phase 1 Jarvis MVP (M3–6), Phase 2 Expansion (M7–12), Phase 3 Enterprise Holarchy (M13–18).
Value proposition: nine capabilities (C1–C9) from 'The Value Jeffrey Brings to Insperity' and the IIH trust model; every project realizes at least one.
Policies & governance: all 142 rules in the SSOT HR Policy Rules Register are assigned to at least one owning project (see Rule Traceability).
Sheets
Projects — one row per project: phase, owner, capabilities, deliverables, KPI, dependencies, rule coverage.
Rule Traceability — one row per project × rule, with statute, domain, type and lifecycle phase from the register.
Coverage — live formulas: projects and rules by phase, domain and capability.
Phase Gates — governance gate criteria each phase must clear before the next is funded.
Companion files
Insperity Solution Architecture.html · Insperity PLM Dashboard.html · Insperity Impact Tracer.html

## Projects
Project ID | Project | Phase | Window | Domain holon | Owner | Priority | Size | Current lifecycle stage | Value-prop capabilities | Summary | Key deliverables | Success KPI | Depends on | Rules owned | Rule IDs | Governing regimes
ISP-01 | Core PEO Ontology (isp-core) & ORSD Templates | Phase 0 · Foundation | Months 1–2 | Enterprise L4 / isp-core | Knowledge Engineer | Critical | M | Deliver | C1 Single source of truth for policy; C7 Governance that scales | Canonical entity model (ClientCompany, Worker, Jurisdiction, EmploymentType, StatutoryStandard) and the owl:imports federation contract every domain holon inherits. | isp-core OWL + SKOS vocabularies; ORSD templates for 6 IP asset types; federation pattern for 5 domain ontologies | Core ontology live; ORSD templates approved | — | 4 | GOV-004, GOV-005, GOV-017, GOV-018 | ISO 8000; OMG ODM/DPROD; LKIF
ISP-02 | SSOT Policy Rules Register & LKIF Wave 1 | Phase 0 · Foundation | Months 1–2 | All L2 domain holons | Compliance Governance Lead | Critical | M | Deliver | C1 Single source of truth for policy; C5 Faster, auditable compliance response | Turns the 142-rule register into governed LKIF obligations, permissions and prohibitions paired with SHACL shapes — the seed library for compilation. | 142 rules keyed and owned; LKIF norms for 4 federal frameworks; rule-to-statute provenance | LKIF library covers 4 frameworks; 100% rules with owner + source | ISP-01 | 8 | PAY-001, PAY-002, PAY-008, BEN-005, CMP-001, TAL-001, GOV-017, GOV-023 | FLSA; Title VII / EEOC; OSHA; ERISA
ISP-03 | Box AI Admission Bridge (33M records → L1 holons) | Phase 0 · Foundation | Months 1–2 | Mediation Holon | Platform Team Lead | High | M | Develop | C1 Single source of truth for policy; C8 Trusted HR assistant (Jarvis, MTBH-governed) | Connects the existing Box AI content cloud to the admission pipeline so plan documents, handbooks and carrier contracts become SHACL-validated knowledge holons. | Admission connector; SHACL admission gate; quarantine + KGCL rejection records | ≥2,000 seed assets admitted; SHACL pass ≥98% | ISP-01 | 2 | GOV-006, GOV-010 | SOC 2; HIPAA Security Rule
ISP-04 | SAML Identity & URI Resolution Registry v1 | Phase 0 · Foundation | Months 1–2 | Mediation Holon | Identity Architect | Critical | S | Develop | C9 Co-employment tenant isolation; C7 Governance that scales | Canonical Worksite Employee and Client Employer entity IDs, resolving payroll, carrier, 401(k), ATS and LMS identifiers before any domain needs them. | Entity ID schemas; resolution service; ISO 8000 uniqueness checks | Canonical IDs for employee & employer; 0 unresolved duplicates in pilot | ISP-01 | 2 | GOV-007, TEC-001 | SOC 2; CCPA/CPRA; ISO 8000
ISP-05 | KGCL Change Governance & Semantic Governance Council Charter | Phase 0 · Foundation | Months 1–2 | Enterprise L4 | Governance Lead | High | S | Deliver | C7 Governance that scales; C5 Faster, auditable compliance response | Five-dimension (WHO/WHAT/WHEN/WHERE/WHY) change records on every triple; DEV/STG/PRD promotion gates; ARB routing for ontology change. | Council charter; KGCL capture live; promotion-gate workflow; MTBH before-state benchmark | 100% ontology changes carry KGCL record | ISP-01 | 3 | GOV-002, GOV-003, GOV-018 | ISO/IEC 42001; NIST AI RMF
ISP-06 | Payroll & Tax Domain Holon (isp-pay) | Phase 1 · Jarvis MVP | Months 3–6 | L2 · Payroll & Tax | Domain Team — Payroll | Critical | L | Design | C1 Single source of truth for policy; C5 Faster, auditable compliance response; C8 Trusted HR assistant (Jarvis, MTBH-governed) | FLSA and state overtime, multi-state wage bases, SUTA/SIT nexus and PFML withholding modeled once and compiled to runtime checks for gross-to-net. | isp-pay ontology; SHACL/SWRL invariants; domain agent; hybrid vector DB; 6 PEPs | Pre-run catch rate ≥99%; manual correction hours −80% | ISP-01, ISP-02, ISP-08 | 21 | PAY-002, PAY-005, PAY-006, PAY-007, PAY-010, PAY-011, PAY-012, PAY-013, PAY-014, PAY-017, PAY-018, PAY-021, PAY-025, PAY-026, PAY-027, CMP-018, PAY-009, PAY-015, PAY-016, PAY-019, PAY-020 | FLSA; State wage & hour codes; SUTA / SIT / local tax; State PFML
ISP-07 | Benefits & Retirement Domain Holon (isp-ben) | Phase 1 · Jarvis MVP | Months 3–6 | L2 · Benefits | Domain Team — Benefits | Critical | L | Design | C1 Single source of truth for policy; C8 Trusted HR assistant (Jarvis, MTBH-governed); C2 Personal-model-driven compliance | Reference implementation of the five-component holon: MEP/PEP fiduciary structure, ACA ALE and affordability logic, SECURE 2.0 eligibility and COBRA events. | isp-ben ontology; ERISA/ACA-grounded PEPs; carrier EDI 834 alignment; GraphRAG index | Benefits answer accuracy ≥98%; stale-answer risk −90% | ISP-01, ISP-02, ISP-03 | 21 | BEN-001, BEN-002, BEN-003, BEN-004, BEN-005, BEN-006, BEN-008, BEN-009, BEN-010, BEN-012, BEN-014, BEN-015, BEN-016, BEN-019, BEN-022, BEN-007, BEN-011, BEN-013, BEN-017, BEN-018, BEN-020 | ERISA; ACA; SECURE 2.0; CAA / TiC / MHPAEA; COBRA; HIPAA
ISP-08 | SHACL-to-Policy Compilation Pipeline | Phase 1 · Jarvis MVP | Months 3–6 | Mediation Holon | Gateway Engineering Lead | Critical | M | Design | C1 Single source of truth for policy; C7 Governance that scales | Six stages — parse, extract, harmonize, target-map, generate, KGCL publish — emitting dbt/SQL tests and OPA/Rego policies with URI traceability to the source norm. | Rule projection agents; compiled policy registry; dbt + Rego emitters | Law change → compiled policy in production ≤5 days; 100% runtime rules carry source URI | ISP-01, ISP-02 | 6 | GOV-001, GOV-019, GOV-020, GOV-022, GOV-024, TEC-021 | SOC 1 (SSAE 18); SOC 2
ISP-09 | Rule Harmonization Engine (most-stringent-rule) | Phase 1 · Jarvis MVP | Months 3–6 | Mediation Holon | Knowledge Engineer | High | S | Define | C1 Single source of truth for policy; C5 Faster, auditable compliance response | SPARQL conflict scans across federal/state/local norms, enforcing highest-employee-protection precedence before any rule is published. | Conflict scan library; precedence model; conflict review queue | 0 unresolved jurisdiction conflicts at publish | ISP-02 | 5 | GOV-008, GOV-009, PAY-002, PAY-004, PAY-026 | FLSA; State wage & hour codes; Municipal minimum wage
ISP-10 | RDSG Gateway, MTBH Circuit Breaker & Simplex Action Gate | Phase 1 · Jarvis MVP | Months 3–6 | L3 · Gateway Holon | Gateway Engineering Lead | Critical | L | Design | C8 Trusted HR assistant (Jarvis, MTBH-governed); C9 Co-employment tenant isolation; C5 Faster, auditable compliance response | Seven-stage traversal: 5D Requirement Context Bundle, PEP evaluation, STPA unsafe-control-action checks, compiled directives, and human sign-off on every irreversible action. | RCB assembler; PEP engine; MTBH 5D scoring; Simplex gate; sanitization queue | Trip rate ≤2%; 100% irreversible actions human-gated | ISP-08, ISP-04 | 9 | GOV-011, GOV-012, GOV-013, GOV-014, GOV-015, GOV-016, GOV-021, PAY-028, PAY-029 | NIST AI RMF; ISO/IEC 42001; STPA/STAMP
ISP-11 | Multi-Tenant Isolation & PHI Policy Enforcement Points | Phase 1 · Jarvis MVP | Months 3–6 | L2 · HR Technology | Security Architect | Critical | M | Design | C9 Co-employment tenant isolation | Tenant boundaries enforced at every data layer and compiled OPA rules for PHI access (role + tenant + MFA), so no client's data ever resolves in another's answer. | Isolation model; compiled RBAC/ABAC policies; immutable audit log | MTBH_WHERE ≥99.5%; 0 cross-tenant incidents | ISP-04, ISP-08 | 8 | TEC-001, TEC-004, TEC-005, TEC-007, TEC-008, TEC-013, TEC-021, BEN-016 | HIPAA Security Rule; SOC 2; CCPA/CPRA
ISP-12 | Employee Jarvis & Machine APIs (pilot, 3–5 clients) | Phase 1 · Jarvis MVP | Months 3–6 | Knowledge services | Product & AI Science | High | L | Define | C8 Trusted HR assistant (Jarvis, MTBH-governed); C2 Personal-model-driven compliance | Self-service answers on PTO, eligibility, open enrollment and pay stubs — every answer trust-scored and traced to the plan clause or statute behind it. | Conversational UI; REST/GraphQL + MCP APIs; provenance display; MTBH dashboard | Self-service deflection ≥40%; P95 ≤3s | ISP-06, ISP-07, ISP-10 | 5 | GOV-014, GOV-021, GOV-022, BEN-021, BEN-022 | NIST AI RMF; ERISA disclosure rules; State privacy acts
ISP-13 | Compliance & Risk Domain Holon (isp-comp, 50-state library) | Phase 2 · Expansion | Months 7–12 | L2 · Compliance & Risk | Domain Team — Compliance | Critical | L | Define | C1 Single source of truth for policy; C5 Faster, auditable compliance response | The full 50-state norm library — recordkeeping, workplace violence, accommodations, leave coordination — compiled to checks that can block a run or flag exposure. | isp-comp ontology; 50-state LKIF norms; OSHA ITA submission rules; accommodation workflows | Audit-evidence time −55%; 0 missed statutory deadlines | ISP-08, ISP-09 | 20 | CMP-001, CMP-002, CMP-003, CMP-004, CMP-006, CMP-007, CMP-010, CMP-011, CMP-012, CMP-013, CMP-016, CMP-017, CMP-019, CMP-021, CMP-008, CMP-009, CMP-014, CMP-015, CMP-020, CMP-022 | OSHA & state plans; CA SB 553; ADA / PWFA / PUMP; State PSL ordinances; Workers' comp / NCCI
ISP-14 | Talent Domain Holon (isp-tal) & AEDT Governance | Phase 2 · Expansion | Months 7–12 | L2 · Talent Management | Domain Team — Talent | High | M | Define | C1 Single source of truth for policy; C4 Continuous values measurement; C5 Faster, auditable compliance response | AEDT bias audits and candidate notices, salary-range disclosure on every posting, FCRA adverse-action sequencing and EEO-1 / state pay-data reporting. | isp-tal ontology; AEDT audit workflow; posting gate; pay-data aggregation | 100% covered postings with compliant range; AEDT audits current | ISP-08, ISP-09 | 13 | TAL-001, TAL-002, TAL-003, TAL-004, TAL-005, TAL-006, TAL-007, TAL-010, TAL-011, TAL-014, TAL-015, TAL-016, TAL-008 | Title VII / ADEA / GINA; NYC LL 144 / Colorado AI Act; Pay transparency laws; FCRA; Form I-9 / E-Verify
ISP-15 | HR Technology Holon — Identity Backbone & Attestation Controls | Phase 2 · Expansion | Months 7–12 | L2 · HR Technology | Domain Team — Platform | High | M | Define | C9 Co-employment tenant isolation; C7 Governance that scales | Full SAML federation of vendor identifiers, masking/tokenization, consent tracking, retention schedules and continuous SOC control evidence. | isp-tech ontology; identity federation; control-evidence feeds; retention engine | SOC evidence assembled continuously; access reviews on schedule | ISP-04, ISP-11 | 14 | TEC-002, TEC-003, TEC-006, TEC-009, TEC-010, TEC-011, TEC-012, TEC-014, TEC-016, TEC-017, TEC-018, TEC-019, TEC-020, TEC-015 | SOC 1 / SOC 2; NIST 800-53; CCPA/CPRA
ISP-16 | Client Relationship Holon & Client Allocation Matrix | Phase 2 · Expansion | Months 7–12 | L2 · Client Relationship | Domain Team — Client Success | Medium | M | Discover | C1 Single source of truth for policy; C6 Analytics you can trust | Models the statutory division of responsibility between Insperity and each client, plus client health scoring and escalation routing. | Allocation Matrix as governed graph; client health model; renewal signals | Every client obligation owned (PEO vs client); at-risk clients flagged ≥60 days out | ISP-02, ISP-04 | 3 | PEO-006, PEO-007, TEC-001 | State PEO licensing / Model PEO Act; MSA contract terms
ISP-17 | Employer/HRBP & Service Rep Jarvis | Phase 2 · Expansion | Months 7–12 | Knowledge services | Product & AI Science | High | M | Discover | C8 Trusted HR assistant (Jarvis, MTBH-governed); C5 Faster, auditable compliance response; C6 Analytics you can trust | Compliance flags, EPLI risk radar and case triage for employers and advisors, grounded only in that client's own MSA and plan documents. | Two role-adapted interfaces; audit-ready evidence packs; case assist | EEOC response prep time −65%; evidence completeness ≥99% | ISP-12, ISP-13, ISP-16 | 4 | GOV-014, GOV-015, GOV-021, PEO-006 | NIST AI RMF; EEOC; EPLI terms
ISP-18 | Governed Personal Models (employee & role profiles) | Phase 2 · Expansion | Months 7–12 | L2 · Talent / isp-core | Knowledge Engineer | High | M | Discover | C2 Personal-model-driven compliance; C4 Continuous values measurement; C9 Co-employment tenant isolation | A governed semantic profile per employee and role — competencies, training and compliance state — queryable and privacy-bounded, with no covert surveillance. | Personal-model ontology; consent + minimization rules; compliance-state queries | Compliance state queryable for 100% of pilot employees | ISP-04, ISP-11 | 5 | TEC-005, TEC-010, TEC-011, TAL-017, TEC-006 | CCPA/CPRA; HIPAA; EEOC
ISP-19 | On-Demand Compliance Training Engine | Phase 2 · Expansion | Months 7–12 | L2 · Talent / Compliance | Domain Team — Talent | Medium | M | Discover | C3 On-demand compliance training; C5 Faster, auditable compliance response; C2 Personal-model-driven compliance | Training assigned automatically when a rule changes or a role changes, against the SSOT rule library — not batched to an annual cycle — with a full audit trail. | Rule-change triggers; LMS integration; completion evidence per rule URI | Training lag after rule change ≤14 days; 100% completion traceable | ISP-18, ISP-08 | 4 | TAL-012, TAL-013, TAL-017, CMP-005 | CA SB 1343; NY harassment training; CA SB 553
ISP-20 | Compliance SSOT Dashboard & Governed Analytics Publishing | Phase 2 · Expansion | Months 7–12 | Mediation Holon | Analytics Lead | Medium | S | Define | C6 Analytics you can trust; C1 Single source of truth for policy | Rules, constraints and definitions compiled once and published into dbt/LookML so every insights dashboard draws on the same governed definitions. | Semantic-layer publishing; SSOT dashboard in production; metric provenance | 100% governed dashboards on shared definitions | ISP-08 | 3 | GOV-006, GOV-023, GOV-022 | SOC 1; DAMA-DMBOK
ISP-21 | MTBH Ops Workbench | Phase 2 · Expansion | Months 7–12 | Governance plane | AI Reliability Lead | High | S | Define | C8 Trusted HR assistant (Jarvis, MTBH-governed); C5 Faster, auditable compliance response | Observability across all six domain holons — 5D trust scores, Value-Drift Coefficient, intent-delta detection and targeted remediation. | Workbench UI; per-domain MTBH; drift alerts; remediation runbooks | MTBH aggregate ≥96% every dimension | ISP-10 | 2 | GOV-014, GOV-011 | NIST AI RMF; ISO/IEC 42001
ISP-22 | Enterprise Semantic Governance Council & Compliance-as-Code | Phase 3 · Enterprise Holarchy | Months 13–18 | Enterprise L4 | Chief Governance Officer | High | S | Discover | C7 Governance that scales; C1 Single source of truth for policy | Formal cross-domain conflict resolution and LKIF norms fully integrated as compliance-as-code across every state Insperity operates in. | Council operating model; conflict protocol; compliance-as-code release train | Cross-domain conflicts resolved within SLA | ISP-05, ISP-13 | 4 | GOV-002, GOV-003, GOV-008, GOV-009 | ISO/IEC 42001; SOC 1 / SOC 2
ISP-23 | Continuous Values Measurement & Calibration | Phase 3 · Enterprise Holarchy | Months 13–18 | L2 · Talent | People Science Lead | Medium | M | Discover | C4 Continuous values measurement; C2 Personal-model-driven compliance | Values training encoded as a versioned rule set, then measured and calibrated continuously as a trust signal — with privacy safeguards and no content-level surveillance. | Values rule set; measurement model; calibration reports; privacy safeguards | eNPS ≥52; values calibration reviewed quarterly | ISP-18, ISP-19 | 4 | TAL-009, TAL-017, TEC-010, TEC-011 | EEOC; CCPA/CPRA; NIST AI RMF
ISP-24 | Self-Evolving Holarchy — Regulatory Change Discovery | Phase 3 · Enterprise Holarchy | Months 13–18 | Mediation Holon | Compliance Governance Lead | High | M | Discover | C5 Faster, auditable compliance response; C7 Governance that scales; C1 Single source of truth for policy | RAG discovery flags newly enacted statutes; domain governance teams validate and admit them via KGCL, updating one domain without touching the others. | Regulatory watch agents; admission workflow; client notification lead time | Time to admit new norm −70%; client notice lead time ×3 | ISP-13, ISP-22 | 4 | GOV-010, GOV-018, CMP-018, CMP-019 | State PFML / PSL; State wage & hour codes
ISP-25 | Executive Jarvis & Workforce Benchmarking Data Product | Phase 3 · Enterprise Holarchy | Months 13–18 | Knowledge services | Product & AI Science | Medium | M | Discover | C6 Analytics you can trust; C8 Trusted HR assistant (Jarvis, MTBH-governed) | Macro workforce trends and regional compensation benchmarking built from de-identified, aggregated data — the first data-marketplace candidate. | Executive dashboard; aggregation + k-anonymity rules; data product | Data product live; 0 re-identification findings | ISP-14, ISP-15, ISP-20 | 3 | TEC-011, TEC-012, TAL-016 | CCPA/CPRA; Antitrust wage-data guidance
ISP-26 | Contractor & Gig Worker Holon (classification governance) | Phase 3 · Enterprise Holarchy | Months 13–18 | L2 · New Ventures | Domain Team — New Ventures | Medium | S | Discover | C1 Single source of truth for policy; C7 Governance that scales | Adds contractor management on the documented extension protocol — no core changes — with ABC-test and economic-reality logic guarding misclassification. | Contractor ontology; classification rules; 1099 reporting | 0 misclassification findings in pilot | ISP-06, ISP-09 | 3 | PAY-003, PAY-004, PAY-022 | DOL economic-reality test; State ABC tests
ISP-27 | PEO Attestation Automation (CPEO · ESAC · SOC) | Phase 3 · Enterprise Holarchy | Months 13–18 | Enterprise L4 | Controller / Internal Audit | High | M | Discover | C5 Faster, auditable compliance response; C6 Analytics you can trust | Assembles CPEO quarterly attestations, ESAC monitoring and SOC evidence straight from rule-level provenance instead of manual evidence hunts. | Attestation evidence packs; bond monitoring; auditor portal | Audit-evidence prep time −60% | ISP-08, ISP-15 | 8 | PEO-001, PEO-002, PEO-003, PEO-004, PEO-005, PAY-023, PAY-024, TEC-016 | IRC §7705 (CPEO); ESAC; SOC 1 / SOC 2
ISP-28 | 50-State Digital Orchestration Rollout | Phase 3 · Enterprise Holarchy | Months 13–18 | Program Office | Program Office | High | L | Discover | C7 Governance that scales; C8 Trusted HR assistant (Jarvis, MTBH-governed) | Full rollout across the expanded client base with carriers, 401(k), ATS and LMS federated through the identity registry. | State-by-state activation plan; ecosystem federation; hypercare | 50 states governed; full client base on the holarchy | ISP-13, ISP-15, ISP-22 | 4 | PAY-013, PAY-014, CMP-017, PEO-007 | All state regimes

## Rule Traceability
Project ID | Project | Phase | Rule ID | Domain | Sub-category | Rule | Rule type | Statute / standard | Jurisdiction | Lifecycle phase | Owning holon
ISP-01 | Core PEO Ontology (isp-core) & ORSD Templates | Phase 0 · Foundation | GOV-004 | Governance & Architecture | Core Ontology | Core Entity Model Definition | Structural Invariant | Root Core PEO Ontology (isp-core) | N/A | Design-Time | Enterprise (L4) / isp-core
ISP-01 | Core PEO Ontology (isp-core) & ORSD Templates | Phase 0 · Foundation | GOV-005 | Governance & Architecture | Ontology Federation | Domain Ontology Federation via owl:imports | Structural Invariant | Federated ontology standard | N/A | Design-Time | L2 Domain Holons
ISP-01 | Core PEO Ontology (isp-core) & ORSD Templates | Phase 0 · Foundation | GOV-017 | Governance & Architecture | Rule Representation | LKIF Deontic Norm + SHACL Shape Dual Representation | Structural Invariant | LKIF Core / W3C SHACL | N/A | Design-Time | L2 Domain Holons (L1 Knowledge Holons)
ISP-01 | Core PEO Ontology (isp-core) & ORSD Templates | Phase 0 · Foundation | GOV-018 | Governance & Architecture | Provenance | Provenance & Change Management - ORSD + KGCL Metadata | Structural Invariant | Ontology Requirements Specification Document (ORSD) / Knowledge Graph Change Language (KGCL) | N/A | Design-Time | Enterprise (L4) / L2 Domain Holons
ISP-02 | SSOT Policy Rules Register & LKIF Wave 1 | Phase 0 · Foundation | PAY-001 | Payroll & Tax | Wage & Hour | Federal FLSA Exemption Salary Threshold & Duties Test | Threshold | FLSA (federal) | Federal | Run | Payroll & Tax Domain Holon (isp-pay)
ISP-02 | SSOT Policy Rules Register & LKIF Wave 1 | Phase 0 · Foundation | PAY-002 | Payroll & Tax | Wage & Hour | State Exemption Salary Thresholds Override Federal | Obligation | State labor codes (e.g., CA, NY, WA) | State (CA, NY, WA, others) | Run | Payroll & Tax Domain Holon
ISP-02 | SSOT Policy Rules Register & LKIF Wave 1 | Phase 0 · Foundation | PAY-008 | Payroll & Tax | Overtime | Federal Weekly Overtime (FLSA 40-hour rule) | Obligation | FLSA (federal) | Federal | Run | Payroll & Tax Domain Holon
ISP-02 | SSOT Policy Rules Register & LKIF Wave 1 | Phase 0 · Foundation | BEN-005 | Benefits | ERISA Fiduciary | Master Plan Document / MEP-PEP Fiduciary Structure | Structural Invariant | ERISA | Federal | Define | Benefits Domain Holon
ISP-02 | SSOT Policy Rules Register & LKIF Wave 1 | Phase 0 · Foundation | CMP-001 | Compliance & Risk | OSHA Recordkeeping | OSHA Form 300/300A/301 Electronic Submission | Reporting Deadline | OSHA Injury Tracking Application (ITA) | Federal (+ State Plans) | Run | Compliance & Risk Domain Holon (isp-comp)
ISP-02 | SSOT Policy Rules Register & LKIF Wave 1 | Phase 0 · Foundation | TAL-001 | Talent Management | Anti-Discrimination | Title VII / ADEA / GINA Hiring Screen | Prohibition | Title VII, ADEA, GINA (federal) | Federal | Discover | Talent Domain Holon (isp-tal)
ISP-02 | SSOT Policy Rules Register & LKIF Wave 1 | Phase 0 · Foundation | GOV-017 | Governance & Architecture | Rule Representation | LKIF Deontic Norm + SHACL Shape Dual Representation | Structural Invariant | LKIF Core / W3C SHACL | N/A | Design-Time | L2 Domain Holons (L1 Knowledge Holons)
ISP-02 | SSOT Policy Rules Register & LKIF Wave 1 | Phase 0 · Foundation | GOV-023 | Governance & Architecture | SSOT Principle | Single Source of Truth (SSOT) Propagation | Structural Invariant | Internal architecture standard | N/A | Design-Time to Run-Time | Enterprise (L4) / Lateral Mediation Holon
ISP-03 | Box AI Admission Bridge (33M records → L1 holons) | Phase 0 · Foundation | GOV-006 | Governance & Architecture | Mediation Layer | Persistent Mapping Graph - Correspondence & Anti-Drift Lineage | Structural Invariant | Lateral Mediation Holon (SAML) | N/A | Design-Time | Lateral Mediation Holon
ISP-03 | Box AI Admission Bridge (33M records → L1 holons) | Phase 0 · Foundation | GOV-010 | Governance & Architecture | AI Grounding | RAG Anchor Index - Vector Embedding Grounding | Structural Invariant | Lateral Mediation Holon (SAML) | N/A | Design-Time | Lateral Mediation Holon
ISP-04 | SAML Identity & URI Resolution Registry v1 | Phase 0 · Foundation | GOV-007 | Governance & Architecture | Identity Resolution | Identity & URI Resolution Registry | Structural Invariant | Lateral Mediation Holon (SAML) / ISO 8000 | N/A | Design-Time | Lateral Mediation Holon
ISP-04 | SAML Identity & URI Resolution Registry v1 | Phase 0 · Foundation | TEC-001 | HR Technology | Multi-Tenancy | Multi-Tenant Data Isolation Model | Structural Invariant | Internal architecture standard / PEO Client Allocation Matrix | N/A | Discover/Design | HR Technology Domain Holon (isp-tech)
ISP-05 | KGCL Change Governance & Semantic Governance Council Charter | Phase 0 · Foundation | GOV-002 | Governance & Architecture | Enterprise Governance | Enterprise Semantic Governance Council & CoE Oversight | Structural Invariant | Internal governance charter | N/A | Design-Time | L4 Enterprise Hierarchy
ISP-05 | KGCL Change Governance & Semantic Governance Council Charter | Phase 0 · Foundation | GOV-003 | Governance & Architecture | Change Management | DEV/STG/PRD Ontology Lifecycle Gate | Structural Invariant | Internal governance charter | N/A | Design-Time | L4 Enterprise Hierarchy
ISP-05 | KGCL Change Governance & Semantic Governance Council Charter | Phase 0 · Foundation | GOV-018 | Governance & Architecture | Provenance | Provenance & Change Management - ORSD + KGCL Metadata | Structural Invariant | Ontology Requirements Specification Document (ORSD) / Knowledge Graph Change Language (KGCL) | N/A | Design-Time | Enterprise (L4) / L2 Domain Holons
ISP-06 | Payroll & Tax Domain Holon (isp-pay) | Phase 1 · Jarvis MVP | PAY-002 | Payroll & Tax | Wage & Hour | State Exemption Salary Thresholds Override Federal | Obligation | State labor codes (e.g., CA, NY, WA) | State (CA, NY, WA, others) | Run | Payroll & Tax Domain Holon
ISP-06 | Payroll & Tax Domain Holon (isp-pay) | Phase 1 · Jarvis MVP | PAY-005 | Payroll & Tax | Overtime | California Daily Overtime - Tier 1 | Obligation | California Labor Code Section 510 | US-CA | Run | Payroll & Tax Domain Holon (isp-pay:CADailyOvertimeNorm)
ISP-06 | Payroll & Tax Domain Holon (isp-pay) | Phase 1 · Jarvis MVP | PAY-006 | Payroll & Tax | Overtime | California Daily Overtime - Tier 2 (Double-Time) | Obligation | California Labor Code Section 510 | US-CA | Run | Payroll & Tax Domain Holon
ISP-06 | Payroll & Tax Domain Holon (isp-pay) | Phase 1 · Jarvis MVP | PAY-007 | Payroll & Tax | Overtime | Alaska & Nevada Daily/24-Hour Overtime Rules | Obligation | AK & NV state labor codes (incl. NV 24-hr rule) | US-AK, US-NV | Run | Payroll & Tax Domain Holon
ISP-06 | Payroll & Tax Domain Holon (isp-pay) | Phase 1 · Jarvis MVP | PAY-010 | Payroll & Tax | Breaks | Meal & Rest Period Penalty Pay | Obligation | State meal/rest break statutes (e.g., CA) | State (varies) | Run | Payroll & Tax Domain Holon
ISP-06 | Payroll & Tax Domain Holon (isp-pay) | Phase 1 · Jarvis MVP | PAY-011 | Payroll & Tax | Multi-State Tax | Multi-State Wage Base & Reciprocal Tax Agreement Logic | Business Logic | State reciprocity agreements | Multi-state | Design | Payroll & Tax Domain Holon
ISP-06 | Payroll & Tax Domain Holon (isp-pay) | Phase 1 · Jarvis MVP | PAY-012 | Payroll & Tax | Multi-State Tax | SUTA Experience Rating Transfer / Allocation | Obligation | State unemployment insurance statutes | Multi-state | Discover/Design | Payroll & Tax Domain Holon
ISP-06 | Payroll & Tax Domain Holon (isp-pay) | Phase 1 · Jarvis MVP | PAY-013 | Payroll & Tax | Multi-State Tax | State Income Tax (SIT) Withholding by Jurisdiction | Obligation | State tax codes | Multi-state | Run | Payroll & Tax Domain Holon
ISP-06 | Payroll & Tax Domain Holon (isp-pay) | Phase 1 · Jarvis MVP | PAY-014 | Payroll & Tax | Multi-State Tax | Local/Municipal Withholding Tax Ordinances | Obligation | Local tax ordinances | Local/Municipal | Run | Payroll & Tax Domain Holon
ISP-06 | Payroll & Tax Domain Holon (isp-pay) | Phase 1 · Jarvis MVP | PAY-017 | Payroll & Tax | Wage Calculation | Court-Ordered Garnishment Priority Engine | Business Logic | Federal/state garnishment statutes | Federal/State | Develop | Payroll & Tax Domain Holon
ISP-06 | Payroll & Tax Domain Holon (isp-pay) | Phase 1 · Jarvis MVP | PAY-018 | Payroll & Tax | Pay Statements | State Wage Theft Prevention Act - Paystub Itemization | Obligation | State wage theft prevention acts | State (varies) | Deliver | Payroll & Tax Domain Holon
ISP-06 | Payroll & Tax Domain Holon (isp-pay) | Phase 1 · Jarvis MVP | PAY-021 | Payroll & Tax | Tax Filing | Federal Form 941 Quarterly Filing | Reporting Deadline | IRS Form 941 | Federal | Run | Payroll & Tax Domain Holon
ISP-06 | Payroll & Tax Domain Holon (isp-pay) | Phase 1 · Jarvis MVP | PAY-025 | Payroll & Tax | Termination | Final Pay Upon Separation - State Timing Rules | Obligation | State final-pay statutes | State (varies) | Run | Payroll & Tax Domain Holon
ISP-06 | Payroll & Tax Domain Holon (isp-pay) | Phase 1 · Jarvis MVP | PAY-026 | Payroll & Tax | Wage Calculation | State/Local Minimum Wage Baseline | Threshold | Federal/state/local minimum wage laws | Federal/State/Local | Define/Run | Payroll & Tax Domain Holon
ISP-06 | Payroll & Tax Domain Holon (isp-pay) | Phase 1 · Jarvis MVP | PAY-027 | Payroll & Tax | Tax Calculation | SUTA/FUTA Annual Wage Base Ceiling | Threshold | IRS/State unemployment tax rules | Federal/State | Run | Payroll & Tax Domain Holon
ISP-06 | Payroll & Tax Domain Holon (isp-pay) | Phase 1 · Jarvis MVP | CMP-018 | Compliance & Risk | Statutory Leave | State PFML Withholding, Reporting & Claims Administration | Obligation | State PFML statutes (MA, WA, NY, NJ, CA, CO, OR, MN, ME, DE, etc.) | State (active PFML states) | Run | Compliance & Risk Domain Holon
ISP-06 | Payroll & Tax Domain Holon (isp-pay) | Phase 1 · Jarvis MVP | PAY-009 | Payroll & Tax | Scheduling | Predictive Scheduling / Fair Workweek Laws | Obligation | State/municipal predictive scheduling ordinances | State/Local (varies) | Design/Develop | Payroll & Tax Domain Holon
ISP-06 | Payroll & Tax Domain Holon (isp-pay) | Phase 1 · Jarvis MVP | PAY-015 | Payroll & Tax | Multi-State Tax | Local Business Registration Nexus Trigger | Threshold | State/local business registration requirements | Local/Municipal | Discover | Payroll & Tax Domain Holon
ISP-06 | Payroll & Tax Domain Holon (isp-pay) | Phase 1 · Jarvis MVP | PAY-016 | Payroll & Tax | Wage Calculation | Tip Credit Accounting | Business Logic | FLSA & state tipped-wage rules | Federal/State | Develop | Payroll & Tax Domain Holon
ISP-06 | Payroll & Tax Domain Holon (isp-pay) | Phase 1 · Jarvis MVP | PAY-019 | Payroll & Tax | Pay Statements | Direct Deposit Mandate Compliance | Obligation | State direct deposit statutes | State (varies) | Deliver | Payroll & Tax Domain Holon
ISP-06 | Payroll & Tax Domain Holon (isp-pay) | Phase 1 · Jarvis MVP | PAY-020 | Payroll & Tax | Pay Statements | Wage Notice Distribution | Obligation | State wage notice statutes | State (varies) | Deliver | Payroll & Tax Domain Holon
ISP-07 | Benefits & Retirement Domain Holon (isp-ben) | Phase 1 · Jarvis MVP | BEN-001 | Benefits | ACA | Applicable Large Employer (ALE) Determination | Business Logic | ACA employer mandate | Federal | Discover | Benefits Domain Holon (isp-ben)
ISP-07 | Benefits & Retirement Domain Holon (isp-ben) | Phase 1 · Jarvis MVP | BEN-002 | Benefits | ACA | Look-Back Measurement Method for Variable-Hour Employees | Business Logic | ACA employer mandate | Federal | Design | Benefits Domain Holon
ISP-07 | Benefits & Retirement Domain Holon (isp-ben) | Phase 1 · Jarvis MVP | BEN-003 | Benefits | ACA | Affordability Safe Harbor Calculation | Threshold | ACA affordability safe harbor rules | Federal | Design | Benefits Domain Holon
ISP-07 | Benefits & Retirement Domain Holon (isp-ben) | Phase 1 · Jarvis MVP | BEN-004 | Benefits | ACA | Annual IRS Form 1094-C/1095-C Generation | Reporting Deadline | ACA employer mandate reporting | Federal | Run | Benefits Domain Holon
ISP-07 | Benefits & Retirement Domain Holon (isp-ben) | Phase 1 · Jarvis MVP | BEN-005 | Benefits | ERISA Fiduciary | Master Plan Document / MEP-PEP Fiduciary Structure | Structural Invariant | ERISA | Federal | Define | Benefits Domain Holon
ISP-07 | Benefits & Retirement Domain Holon (isp-ben) | Phase 1 · Jarvis MVP | BEN-006 | Benefits | ERISA Fiduciary | Form 5500 Annual Filing | Reporting Deadline | ERISA | Federal | Run | Benefits Domain Holon
ISP-07 | Benefits & Retirement Domain Holon (isp-ben) | Phase 1 · Jarvis MVP | BEN-008 | Benefits | ERISA Fiduciary | Annual Non-Discrimination Testing (NDT) | Reporting Deadline | IRC Section 105/125 | Federal | Run | Benefits Domain Holon
ISP-07 | Benefits & Retirement Domain Holon (isp-ben) | Phase 1 · Jarvis MVP | BEN-009 | Benefits | SECURE 2.0 | Mandatory Automatic Enrollment/Escalation | Obligation | SECURE 2.0 Act | Federal | Define | Benefits Domain Holon
ISP-07 | Benefits & Retirement Domain Holon (isp-ben) | Phase 1 · Jarvis MVP | BEN-010 | Benefits | SECURE 2.0 | Long-Term Part-Time (LTPT) Employee Eligibility Tracking | Threshold | SECURE 2.0 Act | Federal | Define | Benefits Domain Holon
ISP-07 | Benefits & Retirement Domain Holon (isp-ben) | Phase 1 · Jarvis MVP | BEN-012 | Benefits | CAA/Transparency | Machine-Readable File (MRF) Disclosure | Obligation | Consolidated Appropriations Act / Transparency in Coverage | Federal | Design | Benefits Domain Holon
ISP-07 | Benefits & Retirement Domain Holon (isp-ben) | Phase 1 · Jarvis MVP | BEN-014 | Benefits | CAA/Transparency | MHPAEA Comparative Analysis | Obligation | Mental Health Parity and Addiction Equity Act | Federal | Design | Benefits Domain Holon
ISP-07 | Benefits & Retirement Domain Holon (isp-ben) | Phase 1 · Jarvis MVP | BEN-015 | Benefits | COBRA | Qualifying Event Notification & Premium Billing | Obligation | COBRA | Federal | Deliver/Run | Benefits Domain Holon
ISP-07 | Benefits & Retirement Domain Holon (isp-ben) | Phase 1 · Jarvis MVP | BEN-016 | Benefits | Data Privacy | HIPAA Privacy/Security Rules for Self-Funded Plans | Structural Invariant | HIPAA | Federal | Run | Benefits Domain Holon; HR Technology Domain Holon
ISP-07 | Benefits & Retirement Domain Holon (isp-ben) | Phase 1 · Jarvis MVP | BEN-019 | Benefits | Integration | Carrier EDI 834 Enrollment Feed Integration | Business Logic | HIPAA 834 EDI standard | Federal (technical standard) | Develop | Benefits Domain Holon
ISP-07 | Benefits & Retirement Domain Holon (isp-ben) | Phase 1 · Jarvis MVP | BEN-022 | Benefits | Enrollment | Qualifying Life Event (QLE) Processing | Business Logic | IRC Section 125 / plan documents | Federal | Run | Benefits Domain Holon
ISP-07 | Benefits & Retirement Domain Holon (isp-ben) | Phase 1 · Jarvis MVP | BEN-007 | Benefits | ERISA Fiduciary | SPD & SMM Disclosure | Obligation | ERISA / DOL electronic disclosure rules | Federal | Deliver | Benefits Domain Holon
ISP-07 | Benefits & Retirement Domain Holon (isp-ben) | Phase 1 · Jarvis MVP | BEN-011 | Benefits | SECURE 2.0 | Emergency Savings Account Integration | Permission | SECURE 2.0 Act | Federal | Define | Benefits Domain Holon
ISP-07 | Benefits & Retirement Domain Holon (isp-ben) | Phase 1 · Jarvis MVP | BEN-013 | Benefits | CAA/Transparency | Pharmacy Benefit Reporting (RxDC) | Reporting Deadline | Consolidated Appropriations Act | Federal | Run | Benefits Domain Holon
ISP-07 | Benefits & Retirement Domain Holon (isp-ben) | Phase 1 · Jarvis MVP | BEN-017 | Benefits | Section 125 | Cafeteria Plan Pretax Elections | Permission | IRC Section 125 | Federal | Define | Benefits Domain Holon
ISP-07 | Benefits & Retirement Domain Holon (isp-ben) | Phase 1 · Jarvis MVP | BEN-018 | Benefits | Section 125 | FSA/HSA Contribution Limit Validation | Threshold | IRC annual FSA/HSA limits | Federal | Develop | Benefits Domain Holon
ISP-07 | Benefits & Retirement Domain Holon (isp-ben) | Phase 1 · Jarvis MVP | BEN-020 | Benefits | Disclosure | Summary of Benefits and Coverage (SBC) Distribution | Obligation | ACA / DOL disclosure rules | Federal | Deliver | Benefits Domain Holon
ISP-08 | SHACL-to-Policy Compilation Pipeline | Phase 1 · Jarvis MVP | GOV-001 | Governance & Architecture | Core Architecture Principle | Definition-Time vs Run-Time Separation | Structural Invariant | Internal Holonic Semantic Governance Architecture standard | N/A - system-wide | Design-Time/Run-Time | Enterprise (L4)
ISP-08 | SHACL-to-Policy Compilation Pipeline | Phase 1 · Jarvis MVP | GOV-019 | Governance & Architecture | Compilation Pipeline | 6-Stage SHACL-to-Policy Compilation Pipeline | Business Logic | Internal Rule Projection Agent tooling | N/A | Design-Time to Run-Time | Lateral Mediation Holon (Rule Projection Agents)
ISP-08 | SHACL-to-Policy Compilation Pipeline | Phase 1 · Jarvis MVP | GOV-020 | Governance & Architecture | Compilation Pipeline | Dual Runtime Target Compilation | Business Logic | Internal Rule Projection Agent tooling | N/A | Run-Time | L3 Gateway Holon / L2 Domain Holons
ISP-08 | SHACL-to-Policy Compilation Pipeline | Phase 1 · Jarvis MVP | GOV-022 | Governance & Architecture | Audit Traceability | Complete Audit Traceability via Immutable URI | Structural Invariant | Internal architecture standard | N/A | Run-Time | L2 Domain Holons / HR Technology Domain Holon
ISP-08 | SHACL-to-Policy Compilation Pipeline | Phase 1 · Jarvis MVP | GOV-024 | Governance & Architecture | Performance Principle | Zero Graph Latency Runtime Principle | Structural Invariant | Internal architecture standard | N/A | Run-Time | L3 Gateway Holon / L2 Domain Holons
ISP-08 | SHACL-to-Policy Compilation Pipeline | Phase 1 · Jarvis MVP | TEC-021 | HR Technology | Runtime Policy | Compiled Runtime Access Policy - HIPAA PHI Read Rule | Structural Invariant | Compiled from isp-tech:HIPAASecurityShape (HIPAA Security Rule) | N/A | Run | HR Technology Domain Holon (OPA/Rego PEP)
ISP-09 | Rule Harmonization Engine (most-stringent-rule) | Phase 1 · Jarvis MVP | GOV-008 | Governance & Architecture | Conflict Resolution | Rule Harmonization Engine - Cross-Jurisdiction Conflict Detection | Business Logic | Lateral Mediation Holon (SAML) / internal SPARQL tooling | N/A - applies across all jurisdictions | Design-Time | Lateral Mediation Holon
ISP-09 | Rule Harmonization Engine (most-stringent-rule) | Phase 1 · Jarvis MVP | GOV-009 | Governance & Architecture | Conflict Resolution | Most-Stringent-Rule / Highest-Employee-Protection Precedence Principle | Structural Invariant | Internal statutory precedence doctrine | N/A - applies across all jurisdictions | Design-Time | Lateral Mediation Holon
ISP-09 | Rule Harmonization Engine (most-stringent-rule) | Phase 1 · Jarvis MVP | PAY-002 | Payroll & Tax | Wage & Hour | State Exemption Salary Thresholds Override Federal | Obligation | State labor codes (e.g., CA, NY, WA) | State (CA, NY, WA, others) | Run | Payroll & Tax Domain Holon
ISP-09 | Rule Harmonization Engine (most-stringent-rule) | Phase 1 · Jarvis MVP | PAY-004 | Payroll & Tax | Worker Classification | State 'ABC' Test for Contractor Status | Prohibition | State statutes (e.g., CA AB5-style ABC tests) | State | Run | Payroll & Tax Domain Holon
ISP-09 | Rule Harmonization Engine (most-stringent-rule) | Phase 1 · Jarvis MVP | PAY-026 | Payroll & Tax | Wage Calculation | State/Local Minimum Wage Baseline | Threshold | Federal/state/local minimum wage laws | Federal/State/Local | Define/Run | Payroll & Tax Domain Holon
ISP-10 | RDSG Gateway, MTBH Circuit Breaker & Simplex Action Gate | Phase 1 · Jarvis MVP | GOV-011 | Governance & Architecture | Request Processing | Requirement Context Bundle (RCB) - 5D Request Decomposition | Business Logic | RDSG Semantic Gateway Protocol | N/A | Run-Time | L3 Gateway Holon (RDSG)
ISP-10 | RDSG Gateway, MTBH Circuit Breaker & Simplex Action Gate | Phase 1 · Jarvis MVP | GOV-012 | Governance & Architecture | Enforcement | Policy Enforcement Points (PEPs) | Structural Invariant | RDSG Semantic Gateway Protocol | N/A | Run-Time | L3 Gateway Holon (RDSG)
ISP-10 | RDSG Gateway, MTBH Circuit Breaker & Simplex Action Gate | Phase 1 · Jarvis MVP | GOV-013 | Governance & Architecture | Safety Verification | STPA/STAMP Unsafe Control Action (UCA) Verification | Structural Invariant | STPA/STAMP safety methodology | N/A | Run-Time | L3 Gateway Holon (RDSG)
ISP-10 | RDSG Gateway, MTBH Circuit Breaker & Simplex Action Gate | Phase 1 · Jarvis MVP | GOV-014 | Governance & Architecture | AI Reliability | Circuit Breaker & MTBH Monitoring | Structural Invariant | RDSG Semantic Gateway Protocol | N/A | Run-Time | L3 Gateway Holon (RDSG)
ISP-10 | RDSG Gateway, MTBH Circuit Breaker & Simplex Action Gate | Phase 1 · Jarvis MVP | GOV-015 | Governance & Architecture | Human Oversight | Simplex Action Gate - Irreversible/Destructive Action Interception | Structural Invariant | RDSG Semantic Gateway Protocol | N/A | Run-Time | L3 Gateway Holon (RDSG)
ISP-10 | RDSG Gateway, MTBH Circuit Breaker & Simplex Action Gate | Phase 1 · Jarvis MVP | GOV-016 | Governance & Architecture | Human Oversight | Simplex Action Gate Threshold - Batch Tax Remittance Example | Threshold | RDSG Semantic Gateway Protocol (illustrative implementation) | N/A | Run-Time | L3 Gateway Holon (RDSG)
ISP-10 | RDSG Gateway, MTBH Circuit Breaker & Simplex Action Gate | Phase 1 · Jarvis MVP | GOV-021 | Governance & Architecture | AI Governance | AI Agent Guardrails - Compiled JSON Schema Constraints | Structural Invariant | RDSG Semantic Gateway Protocol | N/A | Run-Time | L3 Gateway Holon (RDSG)
ISP-10 | RDSG Gateway, MTBH Circuit Breaker & Simplex Action Gate | Phase 1 · Jarvis MVP | PAY-028 | Payroll & Tax | Runtime Control | Simplex Action Gate - High-Value Batch Tax Remittance | Structural Invariant | Internal governance control (STPA/STAMP-informed) | N/A - system control | Run | L3 Gateway Holon (RDSG)
ISP-10 | RDSG Gateway, MTBH Circuit Breaker & Simplex Action Gate | Phase 1 · Jarvis MVP | PAY-029 | Payroll & Tax | Runtime Control | Unsafe Control Action (UCA) Verification on Gross-to-Net | Structural Invariant | STPA/STAMP safety methodology | N/A - system control | Run | L3 Gateway Holon (RDSG)
ISP-11 | Multi-Tenant Isolation & PHI Policy Enforcement Points | Phase 1 · Jarvis MVP | TEC-001 | HR Technology | Multi-Tenancy | Multi-Tenant Data Isolation Model | Structural Invariant | Internal architecture standard / PEO Client Allocation Matrix | N/A | Discover/Design | HR Technology Domain Holon (isp-tech)
ISP-11 | Multi-Tenant Isolation & PHI Policy Enforcement Points | Phase 1 · Jarvis MVP | TEC-004 | HR Technology | Data Privacy | HIPAA Security Rule Compliance | Structural Invariant | HIPAA Security Rule | Federal | Define | HR Technology Domain Holon
ISP-11 | Multi-Tenant Isolation & PHI Policy Enforcement Points | Phase 1 · Jarvis MVP | TEC-005 | HR Technology | Data Governance | Data Classification Rules (PII / PHI / Financial) | Structural Invariant | Internal data governance standard | N/A | Define | HR Technology Domain Holon
ISP-11 | Multi-Tenant Isolation & PHI Policy Enforcement Points | Phase 1 · Jarvis MVP | TEC-007 | HR Technology | Access Control | Role-Based Access Control (RBAC) Governance Baseline | Structural Invariant | Internal security architecture (RBAC/ABAC) | N/A | Design | HR Technology Domain Holon
ISP-11 | Multi-Tenant Isolation & PHI Policy Enforcement Points | Phase 1 · Jarvis MVP | TEC-008 | HR Technology | Audit | Immutable Audit Log Structure | Structural Invariant | Internal architecture standard / SOC 2 requirement | N/A | Design | HR Technology Domain Holon
ISP-11 | Multi-Tenant Isolation & PHI Policy Enforcement Points | Phase 1 · Jarvis MVP | TEC-013 | HR Technology | Access Control | SSO/MFA Secure Endpoint Enforcement | Structural Invariant | Internal security architecture | N/A | Develop | HR Technology Domain Holon
ISP-11 | Multi-Tenant Isolation & PHI Policy Enforcement Points | Phase 1 · Jarvis MVP | TEC-021 | HR Technology | Runtime Policy | Compiled Runtime Access Policy - HIPAA PHI Read Rule | Structural Invariant | Compiled from isp-tech:HIPAASecurityShape (HIPAA Security Rule) | N/A | Run | HR Technology Domain Holon (OPA/Rego PEP)
ISP-11 | Multi-Tenant Isolation & PHI Policy Enforcement Points | Phase 1 · Jarvis MVP | BEN-016 | Benefits | Data Privacy | HIPAA Privacy/Security Rules for Self-Funded Plans | Structural Invariant | HIPAA | Federal | Run | Benefits Domain Holon; HR Technology Domain Holon
ISP-12 | Employee Jarvis & Machine APIs (pilot, 3–5 clients) | Phase 1 · Jarvis MVP | GOV-014 | Governance & Architecture | AI Reliability | Circuit Breaker & MTBH Monitoring | Structural Invariant | RDSG Semantic Gateway Protocol | N/A | Run-Time | L3 Gateway Holon (RDSG)
ISP-12 | Employee Jarvis & Machine APIs (pilot, 3–5 clients) | Phase 1 · Jarvis MVP | GOV-021 | Governance & Architecture | AI Governance | AI Agent Guardrails - Compiled JSON Schema Constraints | Structural Invariant | RDSG Semantic Gateway Protocol | N/A | Run-Time | L3 Gateway Holon (RDSG)
ISP-12 | Employee Jarvis & Machine APIs (pilot, 3–5 clients) | Phase 1 · Jarvis MVP | GOV-022 | Governance & Architecture | Audit Traceability | Complete Audit Traceability via Immutable URI | Structural Invariant | Internal architecture standard | N/A | Run-Time | L2 Domain Holons / HR Technology Domain Holon
ISP-12 | Employee Jarvis & Machine APIs (pilot, 3–5 clients) | Phase 1 · Jarvis MVP | BEN-021 | Benefits | Enrollment | Open Enrollment Self-Service Workflow | Business Logic | Internal plan administration | N/A | Deliver | Benefits Domain Holon
ISP-12 | Employee Jarvis & Machine APIs (pilot, 3–5 clients) | Phase 1 · Jarvis MVP | BEN-022 | Benefits | Enrollment | Qualifying Life Event (QLE) Processing | Business Logic | IRC Section 125 / plan documents | Federal | Run | Benefits Domain Holon
ISP-13 | Compliance & Risk Domain Holon (isp-comp, 50-state library) | Phase 2 · Expansion | CMP-001 | Compliance & Risk | OSHA Recordkeeping | OSHA Form 300/300A/301 Electronic Submission | Reporting Deadline | OSHA Injury Tracking Application (ITA) | Federal (+ State Plans) | Run | Compliance & Risk Domain Holon (isp-comp)
ISP-13 | Compliance & Risk Domain Holon (isp-comp, 50-state library) | Phase 2 · Expansion | CMP-002 | Compliance & Risk | OSHA Recordkeeping | High-Hazard Industry / Covered Size Determination | Threshold | OSHA ITA coverage rules | Federal | Discover | Compliance & Risk Domain Holon
ISP-13 | Compliance & Risk Domain Holon (isp-comp, 50-state library) | Phase 2 · Expansion | CMP-003 | Compliance & Risk | Workplace Violence | CA SB 553 Workplace Violence Prevention Plan | Obligation | California SB 553 | US-CA | Define | Compliance & Risk Domain Holon
ISP-13 | Compliance & Risk Domain Holon (isp-comp, 50-state library) | Phase 2 · Expansion | CMP-004 | Compliance & Risk | Workplace Violence | Violent Incident Log Maintenance | Obligation | California SB 553 | US-CA | Run | Compliance & Risk Domain Holon
ISP-13 | Compliance & Risk Domain Holon (isp-comp, 50-state library) | Phase 2 · Expansion | CMP-006 | Compliance & Risk | Environmental Health | State Heat Illness Prevention Procedures | Obligation | Cal/OSHA, Oregon OSHA, emerging federal OSHA heat rule | US-CA, US-OR, Federal (pending) | Run | Compliance & Risk Domain Holon
ISP-13 | Compliance & Risk Domain Holon (isp-comp, 50-state library) | Phase 2 · Expansion | CMP-007 | Compliance & Risk | Workers' Compensation | Master-Policy Underwriting & Multi-State Risk Pooling | Business Logic | State workers' comp statutes | Multi-state | Run | Compliance & Risk Domain Holon
ISP-13 | Compliance & Risk Domain Holon (isp-comp, 50-state library) | Phase 2 · Expansion | CMP-010 | Compliance & Risk | Workers' Compensation | Workers' Comp Class Codes / NCCI Mapping | Business Logic | National Council on Compensation Insurance (NCCI) | Multi-state | Discover | Compliance & Risk Domain Holon
ISP-13 | Compliance & Risk Domain Holon (isp-comp, 50-state library) | Phase 2 · Expansion | CMP-011 | Compliance & Risk | Accommodations | ADA Interactive Accommodation Process | Obligation | Americans with Disabilities Act | Federal | Design | Compliance & Risk Domain Holon
ISP-13 | Compliance & Risk Domain Holon (isp-comp, 50-state library) | Phase 2 · Expansion | CMP-012 | Compliance & Risk | Accommodations | Pregnant Workers Fairness Act (PWFA) Accommodation Workflow | Obligation | PWFA (federal) | Federal | Design | Compliance & Risk Domain Holon
ISP-13 | Compliance & Risk Domain Holon (isp-comp, 50-state library) | Phase 2 · Expansion | CMP-013 | Compliance & Risk | Accommodations | PUMP Act Lactation Accommodation Policy | Obligation | PUMP for Nursing Mothers Act (federal) | Federal | Design | Compliance & Risk Domain Holon
ISP-13 | Compliance & Risk Domain Holon (isp-comp, 50-state library) | Phase 2 · Expansion | CMP-016 | Compliance & Risk | Leave Coordination | FMLA + State PFML Leave Coordination Logic | Business Logic | FMLA (federal) + State PFML statutes | Federal/State | Develop | Compliance & Risk Domain Holon
ISP-13 | Compliance & Risk Domain Holon (isp-comp, 50-state library) | Phase 2 · Expansion | CMP-017 | Compliance & Risk | Postings | Mandatory Labor Law E-Posting Compliance | Obligation | Federal/state/local posting requirements | Federal/State/Local | Deliver | Compliance & Risk Domain Holon
ISP-13 | Compliance & Risk Domain Holon (isp-comp, 50-state library) | Phase 2 · Expansion | CMP-019 | Compliance & Risk | Statutory Leave | Statutory Paid Sick Leave (PSL) Accrual/Carryover/Front-Loading | Business Logic | Municipal/county PSL ordinances (dozens of disparate rules) | Local/Municipal/County | Define | Compliance & Risk Domain Holon
ISP-13 | Compliance & Risk Domain Holon (isp-comp, 50-state library) | Phase 2 · Expansion | CMP-021 | Compliance & Risk | OSHA Recordkeeping | Annual OSHA Log Certification & Submission | Reporting Deadline | OSHA recordkeeping rule | Federal (+ State Plans) | Run | Compliance & Risk Domain Holon
ISP-13 | Compliance & Risk Domain Holon (isp-comp, 50-state library) | Phase 2 · Expansion | CMP-008 | Compliance & Risk | Workers' Compensation | Drug-Free Workplace Policy Administration | Permission | State drug-free workplace premium credit statutes | State (varies) | Define | Compliance & Risk Domain Holon
ISP-13 | Compliance & Risk Domain Holon (isp-comp, 50-state library) | Phase 2 · Expansion | CMP-009 | Compliance & Risk | Workers' Compensation | Light-Duty / Return-to-Work Accommodation Tracking | Business Logic | State workers' comp / ADA overlap | State (varies) | Run | Compliance & Risk Domain Holon
ISP-13 | Compliance & Risk Domain Holon (isp-comp, 50-state library) | Phase 2 · Expansion | CMP-014 | Compliance & Risk | Accommodations | State Religious/Disability Interactive Process Variants | Obligation | State civil rights statutes | State (varies) | Design | Compliance & Risk Domain Holon
ISP-13 | Compliance & Risk Domain Holon (isp-comp, 50-state library) | Phase 2 · Expansion | CMP-015 | Compliance & Risk | Claims | Digital First Notice of Loss (FNOL) / Claims Intake | Business Logic | Workers' comp claims administration | Multi-state | Develop | Compliance & Risk Domain Holon
ISP-13 | Compliance & Risk Domain Holon (isp-comp, 50-state library) | Phase 2 · Expansion | CMP-020 | Compliance & Risk | Statutory Leave | Statutory Bereavement Leave Tracking | Obligation | State/local bereavement leave statutes | State/Local (varies) | Define | Compliance & Risk Domain Holon
ISP-13 | Compliance & Risk Domain Holon (isp-comp, 50-state library) | Phase 2 · Expansion | CMP-022 | Compliance & Risk | Safety Audits | Client Loss-Control Safety Audits | Business Logic | Internal risk management / workers' comp carrier requirements | N/A | Run | Compliance & Risk Domain Holon
ISP-14 | Talent Domain Holon (isp-tal) & AEDT Governance | Phase 2 · Expansion | TAL-001 | Talent Management | Anti-Discrimination | Title VII / ADEA / GINA Hiring Screen | Prohibition | Title VII, ADEA, GINA (federal) | Federal | Discover | Talent Domain Holon (isp-tal)
ISP-14 | Talent Domain Holon (isp-tal) & AEDT Governance | Phase 2 · Expansion | TAL-002 | Talent Management | Selection Procedures | EEOC Uniform Guidelines on Employee Selection Procedures | Obligation | EEOC Uniform Guidelines | Federal | Discover | Talent Domain Holon
ISP-14 | Talent Domain Holon (isp-tal) & AEDT Governance | Phase 2 · Expansion | TAL-003 | Talent Management | AI Hiring | Automated Employment Decision Tool (AEDT) Bias Audit | Obligation | NYC Local Law 144; Colorado AI Act | NYC; US-CO (+ emerging states) | Design | Talent Domain Holon
ISP-14 | Talent Domain Holon (isp-tal) & AEDT Governance | Phase 2 · Expansion | TAL-004 | Talent Management | AI Hiring | AEDT Candidate Disclosure Notice | Obligation | NYC Local Law 144; Colorado AI Act | NYC; US-CO | Design | Talent Domain Holon
ISP-14 | Talent Domain Holon (isp-tal) & AEDT Governance | Phase 2 · Expansion | TAL-005 | Talent Management | Pay Transparency | State Salary Range Disclosure on Job Postings | Obligation | State pay transparency laws (CA, CO, NY, MA, IL, etc.) | State (varies) | Define | Talent Domain Holon
ISP-14 | Talent Domain Holon (isp-tal) & AEDT Governance | Phase 2 · Expansion | TAL-006 | Talent Management | Pay Transparency | Wage History Ban Enforcement | Prohibition | State wage history ban statutes | State (varies) | Deliver | Talent Domain Holon
ISP-14 | Talent Domain Holon (isp-tal) & AEDT Governance | Phase 2 · Expansion | TAL-007 | Talent Management | Job Design | Standardized Job Description with FLSA Duties Test | Business Logic | FLSA exemption criteria | Federal | Define | Talent Domain Holon
ISP-14 | Talent Domain Holon (isp-tal) & AEDT Governance | Phase 2 · Expansion | TAL-010 | Talent Management | Background Checks | FCRA-Compliant Background Check Consent Workflow | Obligation | Fair Credit Reporting Act (FCRA) | Federal | Develop | Talent Domain Holon
ISP-14 | Talent Domain Holon (isp-tal) & AEDT Governance | Phase 2 · Expansion | TAL-011 | Talent Management | Background Checks | Pre-Adverse / Adverse Action Notice Sequencing | Obligation | FCRA | Federal | Develop | Talent Domain Holon
ISP-14 | Talent Domain Holon (isp-tal) & AEDT Governance | Phase 2 · Expansion | TAL-014 | Talent Management | Employment Verification | Form I-9 / E-Verify Digital Employment Verification | Obligation | Immigration Reform and Control Act / E-Verify | Federal | Deliver | Talent Domain Holon
ISP-14 | Talent Domain Holon (isp-tal) & AEDT Governance | Phase 2 · Expansion | TAL-015 | Talent Management | Reporting | EEO-1 Component 1 Federal Reporting | Reporting Deadline | EEOC EEO-1 reporting rule | Federal | Run | Talent Domain Holon
ISP-14 | Talent Domain Holon (isp-tal) & AEDT Governance | Phase 2 · Expansion | TAL-016 | Talent Management | Reporting | State Pay Data Reporting | Reporting Deadline | CA CRD Pay Data Report; IL Equal Pay Registration Certificate; similar state statutes | US-CA, US-IL (+ others) | Run | Talent Domain Holon
ISP-14 | Talent Domain Holon (isp-tal) & AEDT Governance | Phase 2 · Expansion | TAL-008 | Talent Management | Hiring | Non-Discriminatory Hiring Rubric Standardization | Business Logic | EEOC guidance | Federal | Define | Talent Domain Holon
ISP-15 | HR Technology Holon — Identity Backbone & Attestation Controls | Phase 2 · Expansion | TEC-002 | HR Technology | Attestation | SOC 1 (SSAE 18) Financial Controls Attestation | Structural Invariant | AICPA SSAE 18 / ISAE 3402 | N/A | Define/Run | HR Technology Domain Holon
ISP-15 | HR Technology Holon — Identity Backbone & Attestation Controls | Phase 2 · Expansion | TEC-003 | HR Technology | Attestation | SOC 2 Security/Confidentiality/Availability Attestation | Structural Invariant | AICPA SOC 2 | N/A | Define/Run | HR Technology Domain Holon
ISP-15 | HR Technology Holon — Identity Backbone & Attestation Controls | Phase 2 · Expansion | TEC-006 | HR Technology | Data Privacy | State Data Privacy Statute Compliance (CCPA/CPRA and equivalents) | Obligation | CCPA/CPRA and other state privacy acts | State (varies) | Design | HR Technology Domain Holon
ISP-15 | HR Technology Holon — Identity Backbone & Attestation Controls | Phase 2 · Expansion | TEC-009 | HR Technology | Encryption | Automated Encryption Schema | Structural Invariant | Internal security architecture / HIPAA / SOC 2 | N/A | Design | HR Technology Domain Holon
ISP-15 | HR Technology Holon — Identity Backbone & Attestation Controls | Phase 2 · Expansion | TEC-010 | HR Technology | Consent | Consent Tracking Module | Business Logic | State privacy statutes / HIPAA | State/Federal (varies) | Design | HR Technology Domain Holon
ISP-15 | HR Technology Holon — Identity Backbone & Attestation Controls | Phase 2 · Expansion | TEC-011 | HR Technology | Data Minimization | Data Minimization Algorithm | Business Logic | State privacy statutes / NIST guidance | State/Federal (varies) | Develop | HR Technology Domain Holon
ISP-15 | HR Technology Holon — Identity Backbone & Attestation Controls | Phase 2 · Expansion | TEC-012 | HR Technology | Data Protection | Automated Masking/Tokenization | Structural Invariant | Internal security architecture / PCI-adjacent practice | N/A | Develop | HR Technology Domain Holon
ISP-15 | HR Technology Holon — Identity Backbone & Attestation Controls | Phase 2 · Expansion | TEC-014 | HR Technology | Security Controls | NIST 800-53 Security Control Baseline | Structural Invariant | NIST 800-53 | Federal (framework) | Deliver | HR Technology Domain Holon
ISP-15 | HR Technology Holon — Identity Backbone & Attestation Controls | Phase 2 · Expansion | TEC-016 | HR Technology | Attestation | Continuous SOC 1/SOC 2 Type II Attestation Cycle | Reporting Deadline | AICPA SSAE 18 / SOC 2 | N/A | Run | HR Technology Domain Holon
ISP-15 | HR Technology Holon — Identity Backbone & Attestation Controls | Phase 2 · Expansion | TEC-017 | HR Technology | Security Testing | Vulnerability & Penetration Testing Cadence | Reporting Deadline | Internal security policy / SOC 2 requirement | N/A | Run | HR Technology Domain Holon
ISP-15 | HR Technology Holon — Identity Backbone & Attestation Controls | Phase 2 · Expansion | TEC-018 | HR Technology | Access Control | Periodic Access Review | Business Logic | Internal access governance / SOC 2 | N/A | Run | HR Technology Domain Holon
ISP-15 | HR Technology Holon — Identity Backbone & Attestation Controls | Phase 2 · Expansion | TEC-019 | HR Technology | Data Lifecycle | Data Retention & Destruction Schedule | Obligation | State privacy statutes / internal records policy | State/Federal (varies) | Run | HR Technology Domain Holon
ISP-15 | HR Technology Holon — Identity Backbone & Attestation Controls | Phase 2 · Expansion | TEC-020 | HR Technology | Continuity | Disaster Recovery / Business Continuity (DR/BCP) Audit | Reporting Deadline | Internal BCP policy / SOC 2 availability criteria | N/A | Run | HR Technology Domain Holon
ISP-15 | HR Technology Holon — Identity Backbone & Attestation Controls | Phase 2 · Expansion | TEC-015 | HR Technology | Portal Administration | Self-Service Portal Access & Admin Role Assignment | Business Logic | Internal access governance | N/A | Deliver | HR Technology Domain Holon
ISP-16 | Client Relationship Holon & Client Allocation Matrix | Phase 2 · Expansion | PEO-006 | PEO Operational Standards | Contractual Governance | Client Allocation Matrix - Statutory Responsibility & Liability Division | Structural Invariant | State PEO Licensing Boards / Model PEO Acts | State (varies) | Define | Enterprise (L4)
ISP-16 | Client Relationship Holon & Client Allocation Matrix | Phase 2 · Expansion | PEO-007 | PEO Operational Standards | State Licensing | State PEO Licensing Board Registration Compliance | Obligation | State PEO licensing statutes | State (varies) | Run | Enterprise (L4)
ISP-16 | Client Relationship Holon & Client Allocation Matrix | Phase 2 · Expansion | TEC-001 | HR Technology | Multi-Tenancy | Multi-Tenant Data Isolation Model | Structural Invariant | Internal architecture standard / PEO Client Allocation Matrix | N/A | Discover/Design | HR Technology Domain Holon (isp-tech)
ISP-17 | Employer/HRBP & Service Rep Jarvis | Phase 2 · Expansion | GOV-014 | Governance & Architecture | AI Reliability | Circuit Breaker & MTBH Monitoring | Structural Invariant | RDSG Semantic Gateway Protocol | N/A | Run-Time | L3 Gateway Holon (RDSG)
ISP-17 | Employer/HRBP & Service Rep Jarvis | Phase 2 · Expansion | GOV-015 | Governance & Architecture | Human Oversight | Simplex Action Gate - Irreversible/Destructive Action Interception | Structural Invariant | RDSG Semantic Gateway Protocol | N/A | Run-Time | L3 Gateway Holon (RDSG)
ISP-17 | Employer/HRBP & Service Rep Jarvis | Phase 2 · Expansion | GOV-021 | Governance & Architecture | AI Governance | AI Agent Guardrails - Compiled JSON Schema Constraints | Structural Invariant | RDSG Semantic Gateway Protocol | N/A | Run-Time | L3 Gateway Holon (RDSG)
ISP-17 | Employer/HRBP & Service Rep Jarvis | Phase 2 · Expansion | PEO-006 | PEO Operational Standards | Contractual Governance | Client Allocation Matrix - Statutory Responsibility & Liability Division | Structural Invariant | State PEO Licensing Boards / Model PEO Acts | State (varies) | Define | Enterprise (L4)
ISP-18 | Governed Personal Models (employee & role profiles) | Phase 2 · Expansion | TEC-005 | HR Technology | Data Governance | Data Classification Rules (PII / PHI / Financial) | Structural Invariant | Internal data governance standard | N/A | Define | HR Technology Domain Holon
ISP-18 | Governed Personal Models (employee & role profiles) | Phase 2 · Expansion | TEC-010 | HR Technology | Consent | Consent Tracking Module | Business Logic | State privacy statutes / HIPAA | State/Federal (varies) | Design | HR Technology Domain Holon
ISP-18 | Governed Personal Models (employee & role profiles) | Phase 2 · Expansion | TEC-011 | HR Technology | Data Minimization | Data Minimization Algorithm | Business Logic | State privacy statutes / NIST guidance | State/Federal (varies) | Develop | HR Technology Domain Holon
ISP-18 | Governed Personal Models (employee & role profiles) | Phase 2 · Expansion | TAL-017 | Talent Management | Training | Mandatory Training Completion Tracking | Business Logic | Various statutory training mandates | Federal/State (varies) | Run | Talent Domain Holon
ISP-18 | Governed Personal Models (employee & role profiles) | Phase 2 · Expansion | TEC-006 | HR Technology | Data Privacy | State Data Privacy Statute Compliance (CCPA/CPRA and equivalents) | Obligation | CCPA/CPRA and other state privacy acts | State (varies) | Design | HR Technology Domain Holon
ISP-19 | On-Demand Compliance Training Engine | Phase 2 · Expansion | TAL-012 | Talent Management | Training | Statutory Sexual Harassment Prevention Training Cadence | Reporting Deadline | NY state training mandate; CA SB 1343 | US-NY (annual); US-CA (biannual) | Develop/Deliver | Talent Domain Holon
ISP-19 | On-Demand Compliance Training Engine | Phase 2 · Expansion | TAL-013 | Talent Management | Training | Supervisor vs. Non-Supervisor Differentiated Training Tracks | Business Logic | CA SB 1343 and similar state statutes | State (varies) | Develop | Talent Domain Holon
ISP-19 | On-Demand Compliance Training Engine | Phase 2 · Expansion | TAL-017 | Talent Management | Training | Mandatory Training Completion Tracking | Business Logic | Various statutory training mandates | Federal/State (varies) | Run | Talent Domain Holon
ISP-19 | On-Demand Compliance Training Engine | Phase 2 · Expansion | CMP-005 | Compliance & Risk | Workplace Violence | Annual Workplace Violence Prevention Training | Reporting Deadline | California SB 553 | US-CA | Deliver | Compliance & Risk Domain Holon
ISP-20 | Compliance SSOT Dashboard & Governed Analytics Publishing | Phase 2 · Expansion | GOV-006 | Governance & Architecture | Mediation Layer | Persistent Mapping Graph - Correspondence & Anti-Drift Lineage | Structural Invariant | Lateral Mediation Holon (SAML) | N/A | Design-Time | Lateral Mediation Holon
ISP-20 | Compliance SSOT Dashboard & Governed Analytics Publishing | Phase 2 · Expansion | GOV-023 | Governance & Architecture | SSOT Principle | Single Source of Truth (SSOT) Propagation | Structural Invariant | Internal architecture standard | N/A | Design-Time to Run-Time | Enterprise (L4) / Lateral Mediation Holon
ISP-20 | Compliance SSOT Dashboard & Governed Analytics Publishing | Phase 2 · Expansion | GOV-022 | Governance & Architecture | Audit Traceability | Complete Audit Traceability via Immutable URI | Structural Invariant | Internal architecture standard | N/A | Run-Time | L2 Domain Holons / HR Technology Domain Holon
ISP-21 | MTBH Ops Workbench | Phase 2 · Expansion | GOV-014 | Governance & Architecture | AI Reliability | Circuit Breaker & MTBH Monitoring | Structural Invariant | RDSG Semantic Gateway Protocol | N/A | Run-Time | L3 Gateway Holon (RDSG)
ISP-21 | MTBH Ops Workbench | Phase 2 · Expansion | GOV-011 | Governance & Architecture | Request Processing | Requirement Context Bundle (RCB) - 5D Request Decomposition | Business Logic | RDSG Semantic Gateway Protocol | N/A | Run-Time | L3 Gateway Holon (RDSG)
ISP-22 | Enterprise Semantic Governance Council & Compliance-as-Code | Phase 3 · Enterprise Holarchy | GOV-002 | Governance & Architecture | Enterprise Governance | Enterprise Semantic Governance Council & CoE Oversight | Structural Invariant | Internal governance charter | N/A | Design-Time | L4 Enterprise Hierarchy
ISP-22 | Enterprise Semantic Governance Council & Compliance-as-Code | Phase 3 · Enterprise Holarchy | GOV-003 | Governance & Architecture | Change Management | DEV/STG/PRD Ontology Lifecycle Gate | Structural Invariant | Internal governance charter | N/A | Design-Time | L4 Enterprise Hierarchy
ISP-22 | Enterprise Semantic Governance Council & Compliance-as-Code | Phase 3 · Enterprise Holarchy | GOV-008 | Governance & Architecture | Conflict Resolution | Rule Harmonization Engine - Cross-Jurisdiction Conflict Detection | Business Logic | Lateral Mediation Holon (SAML) / internal SPARQL tooling | N/A - applies across all jurisdictions | Design-Time | Lateral Mediation Holon
ISP-22 | Enterprise Semantic Governance Council & Compliance-as-Code | Phase 3 · Enterprise Holarchy | GOV-009 | Governance & Architecture | Conflict Resolution | Most-Stringent-Rule / Highest-Employee-Protection Precedence Principle | Structural Invariant | Internal statutory precedence doctrine | N/A - applies across all jurisdictions | Design-Time | Lateral Mediation Holon
ISP-23 | Continuous Values Measurement & Calibration | Phase 3 · Enterprise Holarchy | TAL-009 | Talent Management | Performance | Standardized Performance Appraisal Criteria | Business Logic | EEOC / AEDT governance | Federal/State (where AEDT used) | Design | Talent Domain Holon
ISP-23 | Continuous Values Measurement & Calibration | Phase 3 · Enterprise Holarchy | TAL-017 | Talent Management | Training | Mandatory Training Completion Tracking | Business Logic | Various statutory training mandates | Federal/State (varies) | Run | Talent Domain Holon
ISP-23 | Continuous Values Measurement & Calibration | Phase 3 · Enterprise Holarchy | TEC-010 | HR Technology | Consent | Consent Tracking Module | Business Logic | State privacy statutes / HIPAA | State/Federal (varies) | Design | HR Technology Domain Holon
ISP-23 | Continuous Values Measurement & Calibration | Phase 3 · Enterprise Holarchy | TEC-011 | HR Technology | Data Minimization | Data Minimization Algorithm | Business Logic | State privacy statutes / NIST guidance | State/Federal (varies) | Develop | HR Technology Domain Holon
ISP-24 | Self-Evolving Holarchy — Regulatory Change Discovery | Phase 3 · Enterprise Holarchy | GOV-010 | Governance & Architecture | AI Grounding | RAG Anchor Index - Vector Embedding Grounding | Structural Invariant | Lateral Mediation Holon (SAML) | N/A | Design-Time | Lateral Mediation Holon
ISP-24 | Self-Evolving Holarchy — Regulatory Change Discovery | Phase 3 · Enterprise Holarchy | GOV-018 | Governance & Architecture | Provenance | Provenance & Change Management - ORSD + KGCL Metadata | Structural Invariant | Ontology Requirements Specification Document (ORSD) / Knowledge Graph Change Language (KGCL) | N/A | Design-Time | Enterprise (L4) / L2 Domain Holons
ISP-24 | Self-Evolving Holarchy — Regulatory Change Discovery | Phase 3 · Enterprise Holarchy | CMP-018 | Compliance & Risk | Statutory Leave | State PFML Withholding, Reporting & Claims Administration | Obligation | State PFML statutes (MA, WA, NY, NJ, CA, CO, OR, MN, ME, DE, etc.) | State (active PFML states) | Run | Compliance & Risk Domain Holon
ISP-24 | Self-Evolving Holarchy — Regulatory Change Discovery | Phase 3 · Enterprise Holarchy | CMP-019 | Compliance & Risk | Statutory Leave | Statutory Paid Sick Leave (PSL) Accrual/Carryover/Front-Loading | Business Logic | Municipal/county PSL ordinances (dozens of disparate rules) | Local/Municipal/County | Define | Compliance & Risk Domain Holon
ISP-25 | Executive Jarvis & Workforce Benchmarking Data Product | Phase 3 · Enterprise Holarchy | TEC-011 | HR Technology | Data Minimization | Data Minimization Algorithm | Business Logic | State privacy statutes / NIST guidance | State/Federal (varies) | Develop | HR Technology Domain Holon
ISP-25 | Executive Jarvis & Workforce Benchmarking Data Product | Phase 3 · Enterprise Holarchy | TEC-012 | HR Technology | Data Protection | Automated Masking/Tokenization | Structural Invariant | Internal security architecture / PCI-adjacent practice | N/A | Develop | HR Technology Domain Holon
ISP-25 | Executive Jarvis & Workforce Benchmarking Data Product | Phase 3 · Enterprise Holarchy | TAL-016 | Talent Management | Reporting | State Pay Data Reporting | Reporting Deadline | CA CRD Pay Data Report; IL Equal Pay Registration Certificate; similar state statutes | US-CA, US-IL (+ others) | Run | Talent Domain Holon
ISP-26 | Contractor & Gig Worker Holon (classification governance) | Phase 3 · Enterprise Holarchy | PAY-003 | Payroll & Tax | Worker Classification | DOL Multi-Factor Economic Reality Test | Obligation | DOL / Fair Labor Standards Act | Federal | Run | Payroll & Tax Domain Holon
ISP-26 | Contractor & Gig Worker Holon (classification governance) | Phase 3 · Enterprise Holarchy | PAY-004 | Payroll & Tax | Worker Classification | State 'ABC' Test for Contractor Status | Prohibition | State statutes (e.g., CA AB5-style ABC tests) | State | Run | Payroll & Tax Domain Holon
ISP-26 | Contractor & Gig Worker Holon (classification governance) | Phase 3 · Enterprise Holarchy | PAY-022 | Payroll & Tax | Tax Filing | Annual W-2 / 1099-MISC / 1099-NEC Generation | Reporting Deadline | IRS annual information returns | Federal | Run | Payroll & Tax Domain Holon
ISP-27 | PEO Attestation Automation (CPEO · ESAC · SOC) | Phase 3 · Enterprise Holarchy | PEO-001 | PEO Operational Standards | Federal Certification | IRS Certified PEO (CPEO) Status | Structural Invariant | IRC Section 7705 | Federal | Define/Run | Enterprise (L4) / Payroll & Tax Domain Holon
ISP-27 | PEO Attestation Automation (CPEO · ESAC · SOC) | Phase 3 · Enterprise Holarchy | PEO-002 | PEO Operational Standards | Federal Certification | CPEO Annual Independent CPA Audit | Reporting Deadline | IRC Section 7705 | Federal | Run | Enterprise (L4)
ISP-27 | PEO Attestation Automation (CPEO · ESAC · SOC) | Phase 3 · Enterprise Holarchy | PEO-003 | PEO Operational Standards | Federal Certification | CPEO Federal Bonding Requirement | Obligation | IRC Section 7705 | Federal | Run | Enterprise (L4)
ISP-27 | PEO Attestation Automation (CPEO · ESAC · SOC) | Phase 3 · Enterprise Holarchy | PEO-004 | PEO Operational Standards | Industry Accreditation | ESAC Accreditation - Continuous Financial Monitoring | Structural Invariant | Employer Services Assurance Corporation (ESAC) | Industry (national) | Run | Enterprise (L4)
ISP-27 | PEO Attestation Automation (CPEO · ESAC · SOC) | Phase 3 · Enterprise Holarchy | PEO-005 | PEO Operational Standards | Industry Accreditation | ESAC Client Protection Bond Maintenance | Obligation | ESAC | Industry (national) | Run | Enterprise (L4)
ISP-27 | PEO Attestation Automation (CPEO · ESAC · SOC) | Phase 3 · Enterprise Holarchy | PAY-023 | Payroll & Tax | PEO Tax Certification | Quarterly CPEO Tax Attestations | Reporting Deadline | IRC Section 7705 (CPEO) | Federal | Run | Payroll & Tax Domain Holon
ISP-27 | PEO Attestation Automation (CPEO · ESAC · SOC) | Phase 3 · Enterprise Holarchy | PAY-024 | Payroll & Tax | PEO Tax Certification | Surety Bond Maintenance | Obligation | IRC Section 7705 (CPEO) | Federal | Run | Payroll & Tax Domain Holon
ISP-27 | PEO Attestation Automation (CPEO · ESAC · SOC) | Phase 3 · Enterprise Holarchy | TEC-016 | HR Technology | Attestation | Continuous SOC 1/SOC 2 Type II Attestation Cycle | Reporting Deadline | AICPA SSAE 18 / SOC 2 | N/A | Run | HR Technology Domain Holon
ISP-28 | 50-State Digital Orchestration Rollout | Phase 3 · Enterprise Holarchy | PAY-013 | Payroll & Tax | Multi-State Tax | State Income Tax (SIT) Withholding by Jurisdiction | Obligation | State tax codes | Multi-state | Run | Payroll & Tax Domain Holon
ISP-28 | 50-State Digital Orchestration Rollout | Phase 3 · Enterprise Holarchy | PAY-014 | Payroll & Tax | Multi-State Tax | Local/Municipal Withholding Tax Ordinances | Obligation | Local tax ordinances | Local/Municipal | Run | Payroll & Tax Domain Holon
ISP-28 | 50-State Digital Orchestration Rollout | Phase 3 · Enterprise Holarchy | CMP-017 | Compliance & Risk | Postings | Mandatory Labor Law E-Posting Compliance | Obligation | Federal/state/local posting requirements | Federal/State/Local | Deliver | Compliance & Risk Domain Holon
ISP-28 | 50-State Digital Orchestration Rollout | Phase 3 · Enterprise Holarchy | PEO-007 | PEO Operational Standards | State Licensing | State PEO Licensing Board Registration Compliance | Obligation | State PEO licensing statutes | State (varies) | Run | Enterprise (L4)

## Coverage
Portfolio coverage (live formulas)
Phase | Projects | Critical projects | Rule assignments
Phase 0 · Foundation | 5 | 3 | 19
Phase 1 · Jarvis MVP | 7 | 5 | 75
Phase 2 · Expansion | 9 | 1 | 68
Phase 3 · Enterprise Holarchy | 7 | 0 | 30
Total | 28 | 9 | 192
Register domain | Rules in register | Project assignments | Rules uncovered
Payroll & Tax | 29 | 35 | 0
Benefits | 22 | 25 | 0
Compliance & Risk | 22 | 26 | 0
Talent Management | 17 | 21 | 0
HR Technology | 21 | 33 | 0
PEO Operational Standards | 7 | 9 | 0
Governance & Architecture | 24 | 43 | 0
Total | 142 | 192 | 0
Value-prop capability | Projects realizing it
C1 Single source of truth for policy | 14
C2 Personal-model-driven compliance | 5
C3 On-demand compliance training | 1
C4 Continuous values measurement | 3
C5 Faster, auditable compliance response | 12
C6 Analytics you can trust | 5
C7 Governance that scales | 9
C8 Trusted HR assistant (Jarvis, MTBH-governed) | 9
C9 Co-employment tenant isolation | 5

## Register
Rule_ID | Domain | Rule_Name | Assignments
PAY-001 | Payroll & Tax | Federal FLSA Exemption Salary Threshold & Duties Test | 1
PAY-002 | Payroll & Tax | State Exemption Salary Thresholds Override Federal | 3
PAY-003 | Payroll & Tax | DOL Multi-Factor Economic Reality Test | 1
PAY-004 | Payroll & Tax | State 'ABC' Test for Contractor Status | 2
PAY-005 | Payroll & Tax | California Daily Overtime - Tier 1 | 1
PAY-006 | Payroll & Tax | California Daily Overtime - Tier 2 (Double-Time) | 1
PAY-007 | Payroll & Tax | Alaska & Nevada Daily/24-Hour Overtime Rules | 1
PAY-008 | Payroll & Tax | Federal Weekly Overtime (FLSA 40-hour rule) | 1
PAY-009 | Payroll & Tax | Predictive Scheduling / Fair Workweek Laws | 1
PAY-010 | Payroll & Tax | Meal & Rest Period Penalty Pay | 1
PAY-011 | Payroll & Tax | Multi-State Wage Base & Reciprocal Tax Agreement Logic | 1
PAY-012 | Payroll & Tax | SUTA Experience Rating Transfer / Allocation | 1
PAY-013 | Payroll & Tax | State Income Tax (SIT) Withholding by Jurisdiction | 2
PAY-014 | Payroll & Tax | Local/Municipal Withholding Tax Ordinances | 2
PAY-015 | Payroll & Tax | Local Business Registration Nexus Trigger | 1
PAY-016 | Payroll & Tax | Tip Credit Accounting | 1
PAY-017 | Payroll & Tax | Court-Ordered Garnishment Priority Engine | 1
PAY-018 | Payroll & Tax | State Wage Theft Prevention Act - Paystub Itemization | 1
PAY-019 | Payroll & Tax | Direct Deposit Mandate Compliance | 1
PAY-020 | Payroll & Tax | Wage Notice Distribution | 1
PAY-021 | Payroll & Tax | Federal Form 941 Quarterly Filing | 1
PAY-022 | Payroll & Tax | Annual W-2 / 1099-MISC / 1099-NEC Generation | 1
PAY-023 | Payroll & Tax | Quarterly CPEO Tax Attestations | 1
PAY-024 | Payroll & Tax | Surety Bond Maintenance | 1
PAY-025 | Payroll & Tax | Final Pay Upon Separation - State Timing Rules | 1
PAY-026 | Payroll & Tax | State/Local Minimum Wage Baseline | 2
PAY-027 | Payroll & Tax | SUTA/FUTA Annual Wage Base Ceiling | 1
PAY-028 | Payroll & Tax | Simplex Action Gate - High-Value Batch Tax Remittance | 1
PAY-029 | Payroll & Tax | Unsafe Control Action (UCA) Verification on Gross-to-Net | 1
BEN-001 | Benefits | Applicable Large Employer (ALE) Determination | 1
BEN-002 | Benefits | Look-Back Measurement Method for Variable-Hour Employees | 1
BEN-003 | Benefits | Affordability Safe Harbor Calculation | 1
BEN-004 | Benefits | Annual IRS Form 1094-C/1095-C Generation | 1
BEN-005 | Benefits | Master Plan Document / MEP-PEP Fiduciary Structure | 2
BEN-006 | Benefits | Form 5500 Annual Filing | 1
BEN-007 | Benefits | SPD & SMM Disclosure | 1
BEN-008 | Benefits | Annual Non-Discrimination Testing (NDT) | 1
BEN-009 | Benefits | Mandatory Automatic Enrollment/Escalation | 1
BEN-010 | Benefits | Long-Term Part-Time (LTPT) Employee Eligibility Tracking | 1
BEN-011 | Benefits | Emergency Savings Account Integration | 1
BEN-012 | Benefits | Machine-Readable File (MRF) Disclosure | 1
BEN-013 | Benefits | Pharmacy Benefit Reporting (RxDC) | 1
BEN-014 | Benefits | MHPAEA Comparative Analysis | 1
BEN-015 | Benefits | Qualifying Event Notification & Premium Billing | 1
BEN-016 | Benefits | HIPAA Privacy/Security Rules for Self-Funded Plans | 2
BEN-017 | Benefits | Cafeteria Plan Pretax Elections | 1
BEN-018 | Benefits | FSA/HSA Contribution Limit Validation | 1
BEN-019 | Benefits | Carrier EDI 834 Enrollment Feed Integration | 1
BEN-020 | Benefits | Summary of Benefits and Coverage (SBC) Distribution | 1
BEN-021 | Benefits | Open Enrollment Self-Service Workflow | 1
BEN-022 | Benefits | Qualifying Life Event (QLE) Processing | 2
CMP-001 | Compliance & Risk | OSHA Form 300/300A/301 Electronic Submission | 2
CMP-002 | Compliance & Risk | High-Hazard Industry / Covered Size Determination | 1
CMP-003 | Compliance & Risk | CA SB 553 Workplace Violence Prevention Plan | 1
CMP-004 | Compliance & Risk | Violent Incident Log Maintenance | 1
CMP-005 | Compliance & Risk | Annual Workplace Violence Prevention Training | 1
CMP-006 | Compliance & Risk | State Heat Illness Prevention Procedures | 1
CMP-007 | Compliance & Risk | Master-Policy Underwriting & Multi-State Risk Pooling | 1
CMP-008 | Compliance & Risk | Drug-Free Workplace Policy Administration | 1
CMP-009 | Compliance & Risk | Light-Duty / Return-to-Work Accommodation Tracking | 1
CMP-010 | Compliance & Risk | Workers' Comp Class Codes / NCCI Mapping | 1
CMP-011 | Compliance & Risk | ADA Interactive Accommodation Process | 1
CMP-012 | Compliance & Risk | Pregnant Workers Fairness Act (PWFA) Accommodation Workflow | 1
CMP-013 | Compliance & Risk | PUMP Act Lactation Accommodation Policy | 1
CMP-014 | Compliance & Risk | State Religious/Disability Interactive Process Variants | 1
CMP-015 | Compliance & Risk | Digital First Notice of Loss (FNOL) / Claims Intake | 1
CMP-016 | Compliance & Risk | FMLA + State PFML Leave Coordination Logic | 1
CMP-017 | Compliance & Risk | Mandatory Labor Law E-Posting Compliance | 2
CMP-018 | Compliance & Risk | State PFML Withholding, Reporting & Claims Administration | 2
CMP-019 | Compliance & Risk | Statutory Paid Sick Leave (PSL) Accrual/Carryover/Front-Loading | 2
CMP-020 | Compliance & Risk | Statutory Bereavement Leave Tracking | 1
CMP-021 | Compliance & Risk | Annual OSHA Log Certification & Submission | 1
CMP-022 | Compliance & Risk | Client Loss-Control Safety Audits | 1
TAL-001 | Talent Management | Title VII / ADEA / GINA Hiring Screen | 2
TAL-002 | Talent Management | EEOC Uniform Guidelines on Employee Selection Procedures | 1
TAL-003 | Talent Management | Automated Employment Decision Tool (AEDT) Bias Audit | 1
TAL-004 | Talent Management | AEDT Candidate Disclosure Notice | 1
TAL-005 | Talent Management | State Salary Range Disclosure on Job Postings | 1
TAL-006 | Talent Management | Wage History Ban Enforcement | 1
TAL-007 | Talent Management | Standardized Job Description with FLSA Duties Test | 1
TAL-008 | Talent Management | Non-Discriminatory Hiring Rubric Standardization | 1
TAL-009 | Talent Management | Standardized Performance Appraisal Criteria | 1
TAL-010 | Talent Management | FCRA-Compliant Background Check Consent Workflow | 1
TAL-011 | Talent Management | Pre-Adverse / Adverse Action Notice Sequencing | 1
TAL-012 | Talent Management | Statutory Sexual Harassment Prevention Training Cadence | 1
TAL-013 | Talent Management | Supervisor vs. Non-Supervisor Differentiated Training Tracks | 1
TAL-014 | Talent Management | Form I-9 / E-Verify Digital Employment Verification | 1
TAL-015 | Talent Management | EEO-1 Component 1 Federal Reporting | 1
TAL-016 | Talent Management | State Pay Data Reporting | 2
TAL-017 | Talent Management | Mandatory Training Completion Tracking | 3
TEC-001 | HR Technology | Multi-Tenant Data Isolation Model | 3
TEC-002 | HR Technology | SOC 1 (SSAE 18) Financial Controls Attestation | 1
TEC-003 | HR Technology | SOC 2 Security/Confidentiality/Availability Attestation | 1
TEC-004 | HR Technology | HIPAA Security Rule Compliance | 1
TEC-005 | HR Technology | Data Classification Rules (PII / PHI / Financial) | 2
TEC-006 | HR Technology | State Data Privacy Statute Compliance (CCPA/CPRA and equivalents) | 2
TEC-007 | HR Technology | Role-Based Access Control (RBAC) Governance Baseline | 1
TEC-008 | HR Technology | Immutable Audit Log Structure | 1
TEC-009 | HR Technology | Automated Encryption Schema | 1
TEC-010 | HR Technology | Consent Tracking Module | 3
TEC-011 | HR Technology | Data Minimization Algorithm | 4
TEC-012 | HR Technology | Automated Masking/Tokenization | 2
TEC-013 | HR Technology | SSO/MFA Secure Endpoint Enforcement | 1
TEC-014 | HR Technology | NIST 800-53 Security Control Baseline | 1
TEC-015 | HR Technology | Self-Service Portal Access & Admin Role Assignment | 1
TEC-016 | HR Technology | Continuous SOC 1/SOC 2 Type II Attestation Cycle | 2
TEC-017 | HR Technology | Vulnerability & Penetration Testing Cadence | 1
TEC-018 | HR Technology | Periodic Access Review | 1
TEC-019 | HR Technology | Data Retention & Destruction Schedule | 1
TEC-020 | HR Technology | Disaster Recovery / Business Continuity (DR/BCP) Audit | 1
TEC-021 | HR Technology | Compiled Runtime Access Policy - HIPAA PHI Read Rule | 2
PEO-001 | PEO Operational Standards | IRS Certified PEO (CPEO) Status | 1
PEO-002 | PEO Operational Standards | CPEO Annual Independent CPA Audit | 1
PEO-003 | PEO Operational Standards | CPEO Federal Bonding Requirement | 1
PEO-004 | PEO Operational Standards | ESAC Accreditation - Continuous Financial Monitoring | 1
PEO-005 | PEO Operational Standards | ESAC Client Protection Bond Maintenance | 1
PEO-006 | PEO Operational Standards | Client Allocation Matrix - Statutory Responsibility & Liability Division | 2
PEO-007 | PEO Operational Standards | State PEO Licensing Board Registration Compliance | 2
GOV-001 | Governance & Architecture | Definition-Time vs Run-Time Separation | 1
GOV-002 | Governance & Architecture | Enterprise Semantic Governance Council & CoE Oversight | 2
GOV-003 | Governance & Architecture | DEV/STG/PRD Ontology Lifecycle Gate | 2
GOV-004 | Governance & Architecture | Core Entity Model Definition | 1
GOV-005 | Governance & Architecture | Domain Ontology Federation via owl:imports | 1
GOV-006 | Governance & Architecture | Persistent Mapping Graph - Correspondence & Anti-Drift Lineage | 2
GOV-007 | Governance & Architecture | Identity & URI Resolution Registry | 1
GOV-008 | Governance & Architecture | Rule Harmonization Engine - Cross-Jurisdiction Conflict Detection | 2
GOV-009 | Governance & Architecture | Most-Stringent-Rule / Highest-Employee-Protection Precedence Principle | 2
GOV-010 | Governance & Architecture | RAG Anchor Index - Vector Embedding Grounding | 2
GOV-011 | Governance & Architecture | Requirement Context Bundle (RCB) - 5D Request Decomposition | 2
GOV-012 | Governance & Architecture | Policy Enforcement Points (PEPs) | 1
GOV-013 | Governance & Architecture | STPA/STAMP Unsafe Control Action (UCA) Verification | 1
GOV-014 | Governance & Architecture | Circuit Breaker & MTBH Monitoring | 4
GOV-015 | Governance & Architecture | Simplex Action Gate - Irreversible/Destructive Action Interception | 2
GOV-016 | Governance & Architecture | Simplex Action Gate Threshold - Batch Tax Remittance Example | 1
GOV-017 | Governance & Architecture | LKIF Deontic Norm + SHACL Shape Dual Representation | 2
GOV-018 | Governance & Architecture | Provenance & Change Management - ORSD + KGCL Metadata | 3
GOV-019 | Governance & Architecture | 6-Stage SHACL-to-Policy Compilation Pipeline | 1
GOV-020 | Governance & Architecture | Dual Runtime Target Compilation | 1
GOV-021 | Governance & Architecture | AI Agent Guardrails - Compiled JSON Schema Constraints | 3
GOV-022 | Governance & Architecture | Complete Audit Traceability via Immutable URI | 3
GOV-023 | Governance & Architecture | Single Source of Truth (SSOT) Propagation | 2
GOV-024 | Governance & Architecture | Zero Graph Latency Runtime Principle | 1

## Phase Gates
Phase | Window | Gate criteria
Phase 0 · Foundation | Months 1–2 | Gate 0 — ≥2,000 seed IP assets admitted with SHACL validation ≥98%; LKIF library covering FLSA, EEOC, OSHA, ERISA approved; ORSD templates approved for all six IP asset types.
Phase 1 · Jarvis MVP | Months 3–6 | Gate 1 — MTBH_WHERE ≥99.5%, MTBH_WHAT ≥97%, P95 ≤3s, circuit-breaker trip rate ≤2%, self-service deflection ≥40%, zero cross-tenant incidents.
Phase 2 · Expansion | Months 7–12 | Gate 2 — all six domain holons in production, MTBH aggregate ≥96% every dimension, 25–40 client companies, zero unflagged compliance obligations at go-live.
Phase 3 · Enterprise Holarchy | Months 13–18 | Gate 3 — MTBH aggregate ≥97% sustained, zero cumulative cross-tenant breaches, data product live, full 50-state rollout complete.